## Project description
0. Project identification
I. Project title / acronym
Project no 37: Internet-based Geodata Content-Management to foster a River-Basin Related Water Resources Management (INTERRIMA)
II. Lead partner and partnership
|  |  | Institution | [8 empty] | Country
Lead applicant |  |  | Office of Coastal Eng. and Water Mangagment, Ministry of Civil Construction, FHH | [8 empty] | DE
EU Member States involved as project partners | [5 empty] | Non EU Member States involved as project partners
| Denmark: | 0 |  | partner(-s) |  |  | Belarus: |  | 0 | partner(-s)
| Finland: | 2 |  | partner(-s) |  |  | Estonia: |  | 0 | partner(-s)
| Germany: | 3 |  | partner(-s) |  |  | Latvia: |  | 1 | partner(-s)
| Sweden: | 0 |  | partner(-s) |  |  | Lithuania: |  | 0 | partner(-s)
[7 empty] | Norway: |  | 1 | partner(-s)
[7 empty] | Poland: |  | 0 | partner(-s)
[7 empty] | Russia: |  | 0 | partner(-s)
III. Summarised description of the project
III.1 Priority and measure
Measure 1.1 |  |  | Supporting joint strategies and implementation actions for macro-regions
III.2 Central objectives
transnational harmonisation of data organisation and processing for integrative water management of river basins. Transnational co-operation of universities and administration on the field of hydrology and river/coastal hydraulics.Usage of Internet and GIS for cross-disciplinary access to data.
III.3 Expected outcome
a component and internet based open information structure in which geodata of all disciplines relevant for an integrative water management of river basins and geoprocessing tools as well as sophisticated hydrological and hydraulic models are integrated to a geodata and geotool-warehouse.
IV. BSR INTERREG III B project budget | [10 empty] | TOTAL
All amounts in EUR | [10 empty] | 3198000
Amount of ERDF funding applied for | [10 empty] | 1330000
Amount of eligible national co-financing (EU Member States) | [10 empty] | 1330000
Amount of eligible Norwegian national funding applied for | [10 empty] | 269000
Amount of eligible Norwegian regional co-financing | [10 empty] | 269000
V. Project duration
Date of project start |  | Apr/2002 |  |  | Date of project finalisation |  |  | Mar/2005 |  |  | 36 |  | months
VI. PHARE and Tacis funding applied for
Funding from the PHARE programme requested | [7 empty] | no
Funding from the Tacis programme requested | [7 empty] | no
6. Project rationale
6.1. Problem to be addressed
6.1.1. Describe the problem to be addressed.
Environmental problems are in general of multidisciplinary nature, requiring the analyst to examine data from several sources and to apply computation and assessment tools provided by various expert groups. However the administrative institutions which have to provide the data developed indiviual IT-structures resulting in a very heterogeneous geodata landscape which hinders the interdisciplinary and inter-institutional exchange of data and analysis tools. The improvement of interoperability of data sets and analysis tools is one of the main targets to accomplish an integrated water management in the sense of the EU Water Framework Directive. The different administrative entities of data sources need to organize their data in indiviual data warehouses. Their content must be consistent and comparatively among each other to avoid redundance and to guarantee easy cross-disciplinary access.
6.2. Central objectives
6.2.1. What are the central objectives of the project?
Transnational harmonisation of data content, analysis and model application for integrated water management of river basins in the sense of the EU Water Framework Directive. Transnational co-operation of universities and administration focusing on a joint development of Web Services for an internet-GIS portal to access and manage environmental data content from distributed databanks and on the development of hydrological and hydraulic models for system analyis and optimization. Transnational and inter-interstitutional aggreement of techiques on how to transfer information between distributed data sources and models. Improved information and knowledge management in spatial regional planning by providing an easy access to environmental data and results of water resources system analysis.
6.3. Expected outcome
6.3.1. What is the expected outcome of the project?
Implementation of a component and internet based open information structure at the participating administrative institutes. In this innovative system environmental data of all disciplines and processing tools as well as sophisticated hydrological and hydraulic models are integrated to a transnational and cross-disciplinary geodata and geotool-warehouse. In this system a new object orientated data model will be implemented which covers the necessary data content for an integrative water management of river basins in accordance with the EU WaterFramework Directive. The geotool-warehouse integrates the different expertises of the participating universities to an open source shareware of rainfall runoff-modeling and 1- and 2-dimensional hydrodynamic flow modeling.

## Basic info and eligib check
BSR INTERREG III B
First call for project applications 28 September - 17 December 2001
|  | Project title: | Project no 37: INTERRIMA
|  | Lead partner: | Free and Hanseatic City of Hamburg, Germany
|  | Contact person: | Olaf Simon
BASIC INFORMATION AND ELIGIBILITY CRITERIA
No | Section in | Information to be assessed | Eligibility | Ranking | Factual information | Comments
| appl form |  | check | (0, 1, 2, 3) | (yes/no; specification)
1 | 1 | Title/acronym is filled in | Yes
2 | 2.2.1. | An eligible lead partner (only public authorities from the national, regional, sub-regional and local level) is appointed. | Yes
3 | 2.2.2. | In total at least three different eligible countries are involved in the project. | Yes
4 | 2.2.3. | In total at least two partners contribute financially to the total project budget (see Annex V Practical Guide). | Yes
5 | 2.2.4. | At least one of the partners involved in the project comes from an EU Member State. | Yes
6 | 13 | The lead partner confirms that the project has or will not receive any complementary EU funding except from the PHARE and Tacis programmes during the BSR INTERREG III B project period. | Yes
7 | 14.1./14.2. | The lead partner has signed and stamped the application form and the document is submitted as original document. | Yes
8 | 14.3. | A clarification of the lead partner’s signature is given. | Yes
9 | Co-financing statements/Annex I | The budgets presented are confirmed by properly filled in co-financing statements from all partners contributing financially to the budget. | Yes
10 | Co-financing statements | The co-financing statements are presented as original signed and stamped documents. | Yes
11 | Letters of commitment | Partners who are not contributing financially to the project, but still are presented in the partnership list (Annex I) confirm their participation in the project. | No |  |  | Partner 6 has not submitted any letter of commitment.
12 | Letters of commitment /Annex I | The letters of commitment are presented as original signed and stamped documents. | No |  |  | See question no 11.
15 | The application form | The application form (incl annexes) is filled in according to instructions given in the Practical Guide and the Programme Manual. | Yes
Outcome
|  |  |  | Eligibility check | No

## Budget and finances
BSR INTERREG III B
First call for project applications 28 September - 17 December 2001
|  | Project title: | Project no 37: INTERRIMA
|  | Lead partner: | Free and Hanseatic City of Hamburg, Germany
|  | Contact person: | Olaf Simon
BUDGET AND FINANCES
No | Section in | Information to be assessed | Eligibility | Ranking | Factual information | Comments
| appl form |  | check | (0, 1, 2, 3) | (yes/no; specification)
1 | 3.1.1. | The project has applied for funding from the PHARE programme. |  |  | No
2 | 3.1.1. | The project will apply for funding from the PHARE programme. |  |  | No
3 | 3.1.2. | Lead partner(s) of PHARE project. |  |  | Not applicable
4 | 3.1.4. | PHARE programme applied in. |  |  | Not applicable
5 | 3.1.6. | Total budget of the PHARE application applied for. |  |  | Not applicable
6 | 3.1.8. | Progress of application. |  |  | Not applicable
7 | 3.1.9. | Date of approval. |  |  | Not applicable
8 | 3.2.1. | The project has applied for funding from the Tacis programme. |  |  | No
9 | 3.2.1. | The project will apply for funding from the Tacis programme. |  |  | No
10 | 3.2.2. | Lead partner(s) of Tacis project. |  |  | Not applicable
11 | 3.2.4. | Tacis programme applied in. |  |  | Not applicable
12 | 3.2.6. | Total budget of the Tacis project applied for. |  |  | Not applicable
13 | 3.2.8. | Progress of application. |  |  | Not applicable
14 | 3.2.9. | Date of approval. |  |  | Not applicable
15 | 11 | The figures in section 11. correspond to the figures given in Annex IV (automatic transfer of data). | Yes
16 | 12 | The figures in section 12. correspond to the figures given in Annex V (automatic transfer of data). | Yes
17 | Annex I | The individual project budget tables are filled in correctly. | No |  |  | The legal status of the project partners is not used in a consistent way.
18 | Annex I | Number of public organisations participating. |  |  | Ca 4 | See comment in question 17.
19 | Annex I | Public organisations providing national co-financing are eligible (see section 2.1. in the Programme Complement and section 7.2.2. in the Programme Manual) | ?
20 | Annex I | Number of eligible public-like organisations participating. |  |  | Ca 3
21 | Annex I | Public-like organisations providing national co-financing are eligible (see section 2.1. and 5.2.2. of the Programme Complement and section 7.2.3. in the Programme Manual) | ?
22 | Annex I | Number of eligible Norwegian regional organisations participating. |  |  | 1 | Research Institute
23 | Annex I | Norwegian regional organisations (see section 2.1. in the Programme Complement and section 7.2.2. in the Programme Manual) providing national co-financing are eligible. | Yes
24 | Annex I | Number of private organisations participating in the project. |  |  | 0
25 | Annex I | No private non-eligible organisations (see section 5.2.3. of the Programme Complement) are included in the BSR INTERREG III B project budget. | Not applicable
26 | Annex I | Number of partners from objective 1 areas eligible for funding participating in the project. |  |  | 0
27 | Annex I | Partners from objective 1 areas have been cross-checked with national contact points in the various Member States and are eligible for up to 75% BSR INTERREG III B funding. | Not applicable
28 | Annex IV.0 | The budget is structured according to the number of defined work packages | Yes
29 | Annex IV.0 | In case of costs in budget line 6 and 7 Annex IV.1 and IV.2 is filled in. | Yes
30 | Annex IV.0 (Doubled scoring) | The relation between project activity costs (budget line 2, 3, 4, 5, 6, 7) and defined milestones (planned activities and outputs) is realistic (costs effectiveness). |  | 2 |  | The establishment of the data model (WP2 and WP3) constitute more than 60% of the project budget.
31 | Annex IV.0 (Doubled scoring) | The costs for project co-ordination (budget line 1) are relevant in relation to the need for co-ordinating activities of the various work packages (cost effectiveness). |  | 3
32 | Annex IV.0 | The allocation of costs per year is in line with the set up of milestones (planned activities and outputs). |  | 3
33 | Annex IV.1 | Defined other costs (budget line 6) are in line with the project’s objectives, expected outcome, work packages and milestones. |  | 3
34 | Annex IV.2 | Defined investments (budget line 7) are in line with the project’s objectives, expected outcome, work packages and milestones. |  | 3
35 | Annex IV.2 | Specification and size of planned investments. |  |  | EUR 528,000 | IT software and hardware (High costs in relation to other budget items and to the total budget).
36 | Annex V | Public like money from the EU Member States is included in the project budget. |  |  | ? | See comment in question 17.
37 | Annex V | Private money from the EU Member States and NO is included in the project. |  |  | ? | See comment in question 17.
38 | Annex V | PHARE money is included in the total project budget. |  |  | No
39 | Annex V | PHARE money will be included in the total project budget if planned PHARE application will be approved. |  |  | No
40 | Annex V | National/private financing from EE, LV, LT and PL, apart from the PHARE budget, will be included in the total project budget. |  |  | No
41 | Annex V | Tacis money is included in the total project budget. |  |  | No
42 | Annex V | Tacis money will be included in the total project budget |  |  | No
43 | Annex V | National/private financing from BY and RU, apart from the Tacis budget, will be included in the total project budget. |  |  | No
|  |  | TOTAL POINTS: | 19
|  |  | Total available number of points: | 21
|  |  | Scoring: | 3
|  |  | Eligibility: | No
Scoring system
|  |  | No of points | Mark
|  |  | 0-5 | 0
|  |  | 6-10 | 1
|  |  | 11-15 | 2
|  |  | 16-21 | 3

## The project and p-ship
BSR INTERREG III B
First call for project applications 28 September - 17 December 2001
|  | Project title: | Project no 37: INTERRIMA
|  | Lead partner: | Free and Hanseatic City of Hamburg, Germany
|  | Contact person: | Olaf Simon
THE PROJECT AND THE PARTNERSHIP
No | Section in | Information to be assessed | Eligibility | Ranking | Factual information | Comments
| appl form |  | check | (0, 1, 2, 3)
1 | 4.1.1. | The project follows on a BSR INTERREG II C project or has its origin in concepts or strategies developed in a BSR INTERREG II C project. |  |  | No | Linkages to the BSR INTERREG II Cprojects Balticom and Beids, as well as one project INTERREG II C CADSES (Donau).
2 | 4.2.1. | The project has investigated the linkages between the project and operations in other relevant programmes properly. |  | 3
3 | 4.2.1. | There are no overlapping operations between the project applied for and the linkages to other projects or operations in other relevant programmes. |  | 1
4 | 4.3.1. | The project has highlighted the relation between the project and the mentioned policy documents in a correct way and the project is in line with these. |  | 3
5 | 5 | The applicant has chosen the measure that best matches the strategic focus of the project. |  |  | Yes
6 | 6.1.1. (Doubled scoring) | The problem described is relevant to the programme’s direction and focus. |  | 1 |  | Strong focus on water policy and IT only.
7 | 6.2.1. (Doubled scoring) | The objectives of the project correspond to the objectives of the chosen priority/measure (see relevant section in Annex II). |  | 1 |  | The project matches the matters related to water only. The project has almost no relevance for EU-accession. The planning tools are only sectoral. The selected measures are not justified.
8 | 6.2.1. | The objectives (character and number) described are relevant and in relation to the problem described. |  | 1 |  | See comments in question 7.
9 | 6.2.1. | The objectives are consistent in relation to each other. |  | 3
10 | 6.2.1. | The objectives are not contradictory to the overall objectives of the programme. |  | 1 |  | Only water policy is mentioned. Could be seen as a preparatory step for a broader cross-sectoral institutional management.
11 | 6.2.1. | The objectives reflect a significant degree of innovation. |  | 3
12 | 6.3.1. | The expected outcome is relevant and in line with the problem and objectives described. |  | 2
13 | 6.3.1. | The expected outcome reflects a significant degree of innovation. |  | 2
14 | 6.4.1. | The methodology described is clear and in line with the objectives and expected outcome. |  | 3
15 | 6.5.1. | The duration of the project is realistic considering the project’s objectives, expected outcome and the methodology chosen. |  | 3
16 | 6.6.1. | The location of project activities is relevant and in line with the project’s objectives, expected outcome and methodology chosen. |  | 1 |  | There are no accession countries participating in the project's WPs. River basin research in Hamburg?
18 | ANNEX III.0 | The division of work packages is logical and consistent to the central objectives of the project. |  | 1
19 | ANNEX III.0 | The strategic focus of the work packages is relevant and in line with the central objectives of the project. |  | 2
20 | ANNEX III.0 | The planned results of the work packages are realistic and in line with the central objectives of the project. |  | 3
21 | ANNEX III.0 | The accumulated results of all work packages are realistic and in line with the overall objectives of the project. |  | 3
22 | ANNEX III.1-5 | The set up of milestones is realistic in terms of organisation of work and time schedule. |  | 2
23 | 7.3.1. | The project will contribute to equal opportunities as referred to in the BSR INTERREG III B CIP. |  | 1
24 | 7.4.1. (Doubled scoring) | The project will contribute to a sustainable development of the Baltic Sea Region. |  | 1
25 | 9.1.1. /9.1.2./9.1.6. | The final results will be realised and relevant institutions and/or investors have been contacted. |  | 1 |  | The final results will only be realised in Hamburg.
26 | 9.1.4. | The project will be followed up once it has been finalised and will lay ground for further investigation. |  | 1
27 | 9.1.5. | The project will lay ground for large investments. |  |  | Yes
28 | ANNEX I | The composition of the partnership matches the requirements for fulfilling the objectives and for reaching the expected outcome. |  | 1
29 | ANNEX I (Doubled scoring) | The composition of the partnership reflects a vertical representation of institutions and organisations, which is in line with the project's objectives, expected outcome and methodology chosen.. |  | 2 |  | Only for water policy in Hamburg.
30 | 7.1.1. (Doubled scoring) | The level of transnationality (i.e. the number of participating countries) is in line with the project’s objectives, expected outcome and methodology chosen. |  | 1
31 | 7.1.1. | The added value of a transnational approach is well justified. |  | 1
32 | 7.2.1. (Doubled scoring) | The cross-sectoral representation of participating organisations is in line with the project’s objectives, expected outcome and methodology chosen. |  | 1
|  |  | TOTAL POINTS: | 56
|  |  | Total available number of points: | 102
|  |  | Scoring: | 2
Scoring system
|  |  | No of points | Mark
|  |  | 0-24 | 0
|  |  | 25-50 | 1
|  |  | 51-76 | 2
|  |  | 77-102 | 3

## Management and promotion
BSR INTERREG III B
First call for project applications 28 September - 17 December 2001
|  | Project title: | Project no 37: INTERRIMA
|  | Lead partner: | Free and Hanseatic City of Hamburg, Germany
|  | Contact person: | Olaf Simon
MANAGEMENT AND PROMOTION
No | Section in | Information to be assessed | Eligibility | Ranking | Factual information | Comments
| appl form |  | check | (0, 1, 2, 3)
1 | 8.1.1./8.1.2./8.1.3. | The project will promote its activities and final outcome in an efficient way. |  | 2 |  | Not clear how the planning authorities on local/regional level will be targeted.
2 | 10.1.3. | The appointed project co-ordinator is experienced in managing transnational EU-projects. |  | 2
3 | 10.1.6. | The appointed financial manager is experienced in financial management of EU-financed projects. |  | 3
4 | 10.2.1. (Doubled scoring) | The strategic management structure (e.g. decision making principles, the role of a steering group, advisory board etc) is well organised. |  | 1 |  | Broken down per WP. The overall steering of the project is not clarified.
5 | 10.2.2. (Doubled scoring) | The operational management structure (e.g. the day to day management and co-ordination of the work-packages) is well organised. |  | 3
6 | 10.2.3. (Doubled scoring) | The routines for handling and transmitting information from the partners to the six-months reports is well organised. |  | 3
7 | 10.2.4. | A signed contract will be drawn up between the lead partner and the project partners. |  |  | Yes
8 | 10.3.1. (Doubled scoring) | The administrative and financial management of the project is organised in a safe and efficient manner. |  | 2
9 | 10.3.2. | The project’s accounts will be handled (e.g. by the lead partner only, by the lead partner and national key partners, by all partners individually) in a well-organised manner. |  | 2
10 | 10.3.3. | Independent auditors are appointed for securing the correct use of the BSR INTERREG III B funding. |  |  | Yes
|  |  | TOTAL POINTS: | 27
|  |  | Total available number of points: | 36
|  |  | Scoring: | 2
Scoring system
|  |  | No of points | Mark
|  |  | 0-9 | 0
|  |  | 10-18 | 1
|  |  | 19-27 | 2
|  |  | 28-36 | 3

## Sel critieria
BSR INTERREG III B
First call for project applications 28 September - 17 December 2001
Project title: | Project no 37: INTERRIMA
Lead partner: | Free and Hanseatic City of Hamburg, Germany
Contact person: | Olaf Simon
| Yes | No
Support co-operation and integration between EU- and Non-EU countries in the BSR, in particular Central and Eastern European countries; |  | x
Refer to policies adopted for the BSR, e.g. VASAB, Northern Dimension, Baltic 21, and contribute to co-ordination with other initiatives/programmes in the region, and add value to them; | x
Involve the regional and local level to the programme implementation; |  | x
Build on previous experience e.g. results of INTERREG II C projects and other EU programmes (e.g. functioning networks of co-operation); | x
Focus on joint actions towards implementation and on operational measures, e.g. concrete regional project management, pilot and demonstration projects, small scale investments, planning activities preparing investment, such as territorial and environmental impact assessments, expertises, feasibility studies, action and marketing concepts, land use plans; |  | x
Produce results which support economic activities, future investment and job creation; |  | x
Contribute to attracting extra investment and partnership, especially from the private sector; |  | x
Lay the ground for large-scale investment or initiate actions within established national, regional and local systems; | x
Contain elements of system building that have effects beyond the programme period (which are suitable to administer the results of the projects, continue to build on them and contribute towards a long-term accumulation of knowledge); | x
Contribute to development of methods for strengthening the gender perspective; |  | x
Include the presentation of quantified outputs to allow for appraisal and ex-post evaluation; | x
Are able to demonstrate innovative approach and concrete, visible results and disseminate best practice; |  | x
Have a well defined and appropriate transnational partnership; |  | x
Have an appropriate size, number of partners and duration (see recommendations for project design). |  | x

## A-sheet
BSR INTERREG III B
First call for project applications 28 September - 17 December 2001
Project title: | Project no 37: INTERRIMA
Lead partner: | Free and Hanseatic City of Hamburg, Germany
Contact person: | Olaf Simon
ASSESSMENT SHEET
Basic information and eligibility criteria
Eligibility check passed |  | No
Comments
The letter of commitment for partner no 6 has not been submitted.
Budget and finances
Mark in assessment of application: |  | A
Comments
No remarks apart from that the legal status of the listed partners is not stated in a consistent way, which leads to an incorrect picture of the financial structure. The project has furthermore budgeted relatively high costs for IT equipment only.
The project and the partnership
Mark in assessment of application: |  | B
Comments
The project is focussed on an application of the EU water framework directive and development of a hydrological GIS model. The project is despite an integrated approach on water management very mono-sectoral in relation to the programme's strategic objectives. The outcome is mainly concentrated to isolated interests in Germany. The project is therefore of less transnational relevance and is rather of a technical nature with weak connections to spatial planning and regional development in practice.
Management and promotion
Mark in assessment of application: |  | B
Comments
No special remarks apart from that there is no information given on how the overall steering mechanism of the project would be handled.
Recommendation |  | No
The project is not recommended to be approved because of its too mono-sectoral approach and technical character. The project focuses on water management and is relatively isolated to single interests. The project has furthermore a too strong focus on investigation in Germany. In addition to this the partnership is imbalanced and demonstrates a limited transnational value. The project could be characterised as a technical project with limited links to practical application on regional development and planning.